ZIKO Human Resources Tracking

Internal survey proposal

1. Context & Objectives

Ziko Apteka would like to carry out an internal research to measure the internal climate of the company. The overall goal is to provide information about the views of staff members within the organisation. The results will provide management with information to assist in decision-making and provide alerts to areas requiring urgent attention.

The types of issues covered in the survey may include:

- The work environment and the enjoyment of work (overall satisfaction, Promotional possibilities, career progression, relevance of work to business objectives, etc.)

- Feeling of rewards and recognition

- Perception regarding the management team (practices, strategy and vision)

- Image of the company (overall and in detail)

- Perception of the internal communication (satisfaction, understanding, expectations, etc.)

The concrete objectives of the project will be discuss with the person in charge of the project in Ziko in order to set up a questionnaire that fits the needs and to provide concrete and operational information.

2. Answer

Methodology :

We recommend to carry out an online interviewing via emailing to Ziko employees a link to the questionnaire. This emailing should preferably be conducted as an outsourced process to remove suspicion about privacy and confidentiality and the use of results, and provide a trusted environment. This is essential to get staff to answer the survey honestly, thereby giving the best possible information.

This online interviewing will be possible only if all the employees have a private access to internet and if Ziko can provide the whole of the employees’ addresses.

If an online interviewing is not possible, we propose to carry out the survey with a paper mailing (more expensive as we will have to provide stamps and envelopes).

Target population: 200 Ziko Apteka employees

Periodicity:  One shot Survey or annual barometer

Questionnaire: A 12 minutes interview in order to maximize the feedback rate (usually the feedback rate is between 60% and 80%). This corresponds to 20 questions with 1 or 2 open-ended questions (see the questionnaire example).

Planning: 5 weeks starting after client’s agreement:

| STAGE | Electronic fieldwork | Paper fieldwork |
| --- | --- | --- |
| - Project agreement - Questionnaire agreement - Beginning of fieldwork - End of fieldwork - Data processing - Presentation with synthesis | 2010/10/04 10/08 10/12 10/26 10/29 11/04 | 2010/10/04 10/08 10/12 11/01 11/05 11/10 |

Nicolas Curtelin’s responsibilities:

- Questionnaire writing in French

- Control of the process and fieldwork management

- Database creation (questionnaires digitization in case of paper interview)

- Data processing and statistical analysis

- PowerPoint presentation and synthesis (in French)

Ziko’s responsibilities:

- Questionnaire translation

- Email addresses to be provided in case of electronic questionnaire

- Envelopes and stamps to be provided in case of paper questionnaire

Data processing and deliverable:

The final data set can be weighted in order to fit better the reality.

For example according to the distribution of workers within each pharmacy, or according to the workers’ status (managers vs. employees) or according to the profit of the different pharmacies.

The final presentation will include overall results of the survey and cross tabs according to specific populations:

- Differences according to the pharmacy units;

- Differences according to regional breakdowns (Krakow vs. Warsaw);

- Differences according to the socio demographical criteria (gender, age, level of education, etc.);

- Differences according to the working status (seniority, managers vs. employees, etc.)

We will also carry out secondary analysis which will help to identify the main improvements drivers (for example the matrix measuring the impact of the different working issues on the overall satisfaction). This is helpful to identify areas requiring managerial input.

Importance of the communication:

Communication is the most important aspect of such a project and must be conducted at all the steps of the process.

Communication before the interviewing:

It is important to explain the staff the objectives of the survey (to improve our way of working together, to take into consideration your expectations, etc.)

This is essential to get staff to answer the survey honestly, thereby giving the best possible information. That’s why it is important to insist on the fact the project is conducted as an outsourced process and that anonymity is guaranteed (Ziko managers will only get percentages).

Communication after the interviewing:

Measurement will de-motivate staff if no action is apparent after the survey. Managers must ensure that the views of staff are acted upon, and areas requiring improvement are addressed and any actions taken are communicated clearly to staff.

It is best practice for the survey results to be transparent and publishing the results for staff to view is very motivating.

3. Costs estimate:

|  | PAPER | EMAIL |
| --- | --- | --- |
| Set Up costs | 200 | 200 |
| Questionnaire drawing writing in French | 300 | 300 |
| Control of the process and fieldwork management | 150 | 300 |
| Database creation (questionnaires digitization) | 400 |  |
| Data processing and statistical analysis | 500 | 500 |
| PowerPoint presentation and synthesis (in French) | 600 | 600 |
| TOTAL NICOLAS CURTELIN | 2150 | 1900 |
| Fieldwork |  |  |
| Questionnaire electronic (Estimate - External provider) |  | 2500 |
| 200 Stamps*1,7 Zl | 340 |  |
| 200*3 pages printing | 300 |  |
| TOTAL | 640 | 2500 |
| TOTAL (zl without VAT) | 2790 | 4400 |